## Manual Chart
Team #6 - Trashcan Productions
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 12 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Server & Client
| Server Programming | 2019-04-25 | 2019-04-30 | 4 | Filipa,Ivo | 100% | bar: WEEK 14 Th to WEEK 15 T
| Client Programming | 2019-04-25 | 2019-04-30 | 4 | Filipa,Ivo | 100% | bar: WEEK 14 Th to WEEK 15 T
| Implementing Network into game | 2019-04-17 | 2019-04-17 | 1 | Ivo | 100%
| Network Testing | 2019-04-25 | 2019-05-01 | 5 | Filipa | 100% | bar: WEEK 14 Th to WEEK 15 W
| Documentation | 2019-04-11 | 2019-04-12 | 2 | Filipa,Saelda | 100% | bar: WEEK 12 Th to WEEK 12 F; WEEK 14 Th to WEEK 14 F; WEEK 15 F
|  |  |  | 0 |  | 0%
Chat
| Chat GUI | 18/4/2019 | 18/4/2019 | 1 | Filipa,Saelda | 100%
| Chat Functionality | 2019-04-25 | 2019-04-28 | 2 | Filipa,Ivo | 100%
| Chat works w/ Server/Client | 2019-04-25 | 2019-04-28 | 2 | Ivo | 100% | bar: WEEK 14 Th to WEEK 15 T
| Testing | 2019-04-27 | 2019-05-01 | 3 | Filipa,Ivo | 100% | bar: WEEK 14 Th to WEEK 15 W
Quiz Quest
| Game works as intended | 2019-04-28 | 2019-04-28 | 0 | Filipa,Ivo | 100% | bar: WEEK 14 T
| Testing | 2019-04-30 | 2019-04-30 | 1 | Filipa,Ivo | 100% | bar: WEEK 14 T
| Question class works | 2019-05-27 | 2019-05-28 | 2 | Ivo | 100% | bar: WEEK 14 W to WEEK 14 Th
|  | 2019-04-26 | 2019-04-26 | 1 | Filipa | 0% | bar: WEEK 14 F to WEEK 15 T
|  |  |  | 0 |  | 0% | bar: WEEK 14 F; WEEK 15 T
|  |  |  | 0 |  | 0%
Extra stuff (optional)
| Server GUI | 2019-04-30 | 2019-04-30 | 1 | Filipa | 100%
| Client Login GUI | 2019-05-01 | 2019-05-01 | 1 | Filipa | 100%
0 | bar: WEEK 15 M to WEEK 15 W
0
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])